## Slide 1
PITCHROOM AI / EVERYDAY WORK
SYNTHETIC SAMPLE · SAFE TO EXPLORE
Northstar Retail
A 30-day analytics onboarding plan
Use this deck to practise questions, check the cited slide, and try a spoken answer.
VOICE
Ask naturally
EVIDENCE
Check the slide
PRACTICE
Rehearse the answer
SYNTHETIC PRACTICE SCENARIO
CUSTOMER SUCCESS 01 / 06

## Slide 2
CUSTOMER SUCCESS
Customer kickoff
Practice account · All company and usage details are fictional
01
Customer goal
Give retail operations leads one reliable view of weekly store performance.
02
Initial group
Start with 18 operations and finance users across four stores.
03
Agreed outcome
By day 30, at least 14 of the 18 users can find and explain their weekly store report.
04
Working decision
Run a guided 30-day pilot before discussing a wider rollout.
SYNTHETIC PRACTICE SCENARIO
CUSTOMER SUCCESS 02 / 06

## Slide 3
CUSTOMER SUCCESS
Success measures
Agree how both sides will judge the pilot
01
Access
All 18 invited users can sign in by day 5.
02
Adoption
At least 14 users review the weekly report twice by day 30.
03
Report trust
Finance signs off on the sales and returns definitions in week two.
04
Closeout
The customer and account lead review usage, unresolved issues, and rollout readiness.
SYNTHETIC PRACTICE SCENARIO
CUSTOMER SUCCESS 03 / 06

## Slide 4
CUSTOMER SUCCESS
30-day milestones
The customer knows what happens next
01
Day 1 · Kickoff
Confirm the goal, four-store scope, owners, access list, and meeting times.
02
Day 5 · First use
Complete access setup and the first guided report review.
03
Day 14 · Midpoint
Validate sales and returns definitions with finance; resolve reporting gaps.
04
Day 30 · Review
Check the agreed adoption outcome and decide whether to extend or expand.
SYNTHETIC PRACTICE SCENARIO
CUSTOMER SUCCESS 04 / 06

## Slide 5
CUSTOMER SUCCESS
Owners and cadence
Clear responsibility on both sides
01
Customer sponsor · Asha
Approves scope, makes store leads available, and joins the midpoint and closeout.
02
Customer operator · Luis
Shares sample workflows and gathers store-team feedback.
03
Account lead · Priya
Coordinates the plan, tracks risks, and sends a written weekly recap.
04
Support · Shared queue
Log product issues in the customer queue; urgent sign-in blocks go to support the same day.
SYNTHETIC PRACTICE SCENARIO
CUSTOMER SUCCESS 05 / 06

## Slide 6
CUSTOMER SUCCESS
Risks and next steps
Actions for the coming week
01
Data definition
Sales and returns use different finance definitions. Finance will approve them by day 10.
02
Low participation
Store schedules can prevent training. Offer two 20-minute sessions per week.
03
Access
The customer admin sends the 18-user list two business days before kickoff.
04
Next meeting
The weekly check-in is Thursday at 10:00; Priya shares the decisions and owners afterward.
SYNTHETIC PRACTICE SCENARIO
CUSTOMER SUCCESS 06 / 06