## Slide 1
PITCHROOM AI / EVERYDAY WORK
SYNTHETIC SAMPLE · SAFE TO EXPLORE
Northstar release
A weekly product launch update
Use this deck to practise questions, check the cited slide, and try a spoken answer.
VOICE
Ask naturally
EVIDENCE
Check the slide
PRACTICE
Rehearse the answer
SYNTHETIC PRACTICE SCENARIO
PROJECT DELIVERY 01 / 06

## Slide 2
PROJECT DELIVERY
Weekly project update
Week of 14 July · Fictional product team
01
Overall status
Amber. Core reporting is ready; the export and access checks need attention.
02
Target
Start a controlled customer pilot on 24 July with 12 invited teams.
03
Shipped
Seven of eight priority dashboard views passed product review.
04
Decision
Keep the pilot date, then limit onboarding if export is still blocked on 21 July.
SYNTHETIC PRACTICE SCENARIO
PROJECT DELIVERY 02 / 06

## Slide 3
PROJECT DELIVERY
Milestones and owners
The next five working days
01
CSV export fix · Mei · 18 Jul
A date-format bug prevents finance teams from using the downloaded report.
02
Access review · Ravi · 19 Jul
Confirm role permissions with Security before inviting pilot users.
03
Pilot guide · Sam · 21 Jul
Prepare the 30-minute setup call and a first-week checklist.
04
Pilot launch · Jordan · 24 Jul
Invite 12 opted-in teams when export and access checks pass.
SYNTHETIC PRACTICE SCENARIO
PROJECT DELIVERY 03 / 06

## Slide 4
PROJECT DELIVERY
What is blocking launch?
Two checks have named owners
01
Export issue
The CSV date bug is the main launch blocker. Mei owns the fix; a retest is due 18 July.
02
Role check
Security has not confirmed one read-only permission path. Ravi owns the review by 19 July.
03
Fallback
If either check fails on 21 July, onboard six teams first and hold the remaining invites.
04
Decision owner
Jordan can keep or reduce the pilot after reviewing the two test results.
SYNTHETIC PRACTICE SCENARIO
PROJECT DELIVERY 04 / 06

## Slide 5
PROJECT DELIVERY
Risks and decisions
What changed this week
01
Scope
Bulk editing moved out of the pilot. The first release includes saved views, filters, and CSV export.
02
Capacity
Two engineers are available for launch work. No additional launch staffing is assumed.
03
Customer impact
The export fix affects finance workflows; the access review affects all pilot roles.
04
Escalation
Raise a blocker in the team channel the same day; Jordan schedules a 15-minute decision review.
SYNTHETIC PRACTICE SCENARIO
PROJECT DELIVERY 05 / 06

## Slide 6
PROJECT DELIVERY
Next seven days
A short sequence to protect the pilot
01
18 July
Retest export with three date formats and a finance sample.
02
19 July
Record the Security permission decision and retest each pilot role.
03
21 July
Review both checks; choose 12 or six teams for the first wave.
04
24 July
Run pilot setup calls and collect the first-day issues in the shared tracker.
SYNTHETIC PRACTICE SCENARIO
PROJECT DELIVERY 06 / 06